## Slide 1: Software Requirement Engineering (SE-211)
Lecture 28: Estimation

## Slide 2: Estimation
Experience and Beware of the Sales Guy

## Slide 3: Cost Estimation
Project scope must be explicitly defined
Task, functional, or component decomposition is necessary
Historical measures (metrics) are very helpful
To assure fit, use two or more estimation techniques
Uncertainty is inherent in most estimation endeavors – plan on it!

## Slide 4: Planning Poker is a consensus-based estimation technique used by Agile teams globally.

## Slide 5: Step-01: Organization of the game
Full team will involve in Planning Poker game.
Will require 2–4 hours
Also require a large table where all members will sit.
Each team member will have a set of cards
In each card set there will have 10 cards with numbering 0, 1, 2, 3, 5, 8, 13, 21, 40 and 100 i.e. 1st card’s no will 0, 2nd card’s no will 1, 3rd card’s no will 2, 4th card’s no will 3, 5th will 4, 6th will 8, 7th will 13, 8th will 21, 9th will 40 and 10th will 100

## Slide 6: Step-02: Introducing Story by Product Owner
The Product Owner introduces the user story by talking about:
The motivation for doing the user story.
The intended outcome and benefits.
The scope of the user story (including what is not in scope with this user story).
Other relevant considerations.

## Slide 7: Step-03: Discussing about the Story
What should happen in a given scenario?
What should happen in some negative case or edge case (i.e. plausible but not common scenario)?
Do we need to build this for one type, several user types or all users?
Do we need to track any new performance metrics in order to understand if this user story is working as expected?

## Slide 8: Step-04: Playing Cards
After discussion team members will ask to point for that story i.e. Product owner will ask them Now Select your card for assign Story Point to this story
Each team member will select their card and put it on the table with face down, so that others can’t see his/her point.

## Slide 9: Step-05: Achieving Consensus
Most of the time one thing will identify which is a huge mismatch between given numbers.
In that case members with highest and lowest numbers will ask why their chose estimates
They will give some justification and discuss with the team regarding this issue. This will also help the team if they have any misunderstanding or vogue idea about the story and adjusting their estimation
After justification the process i.e. Step-04 will continue again
This process will continue until all members agrees to a common estimate
Once all team members agrees to a common estimate then Product owner will record that point and go for next story and will continue from step-02 to step-05
If after 5–6 rounds of playing the game estimation fail meet all members agreement then put it aside for revisit later

## Slide 11
HOW IT WORKS

## Slide 12
HOW IT WORKS

## Slide 13
HOW IT WORKS

## Slide 14
HOW IT WORKS

## Slide 15
HOW IT WORKS

## Slide 16
HOW IT WORKS

## Slide 17
HOW IT WORKS

## Slide 18
HOW IT WORKS

## Slide 19
HOW IT WORKS

## Slide 20
HOW IT WORKS

## Slide 21
DISAGREEMENTS
HOW TO GET THE FINAL ESTIMATE
  Keep voting until everyone votes the same number
  Keep voting until estimates are “close enough” and average them
  Average the votes even if they’re not very close
  When averaging, keep exact average or round up

## Slide 22
DISAGREEMENTS
HOW TO GET THE FINAL ESTIMATE
NUMBER SEQUENCING
  Playing Cards:
    Ace, 2, 3, 4, 5, 6… King
  Modified Fibonacci:
    0, ½, 1, 3, 5, 8, 13, 20, 40, 100
  Sequential:
    0, ½, 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 15…
  T-Shirt Sizes:
    xxs, xs, s, m, l, xl, xxl
  With Icons:
    Infinity means it can’t be done, coffee cup means I need a break
  And what do the numbers mean? Story points, ideal days, etc.

## Slide 23
DISAGREEMENTS
HOW TO GET THE FINAL ESTIMATE
NUMBER SEQUENCING
TO TIME OR NOT TO TIME
  Original purpose was to keep estimation meetings moving (Agile Alliance)
  Use a timer to limit each round?
  Use a timer to limit vote justifications?
  How long to set in both cases?

## Slide 24
DISAGREEMENTS
HOW TO GET THE FINAL ESTIMATE
NUMBER SEQUENCING
TO TIME OR NOT TO TIME
?

## Slide 25
BENEFITS
Promotes accuracy, prevents bias
Keeps things organized & moving
Can assist in task assignment
Allows for multiple timelines based on cuts

## Slide 26
196
RAW MATH
6 Devs
5 days/week
30 points/week
196/30 = 6.4 weeks!

## Slide 28
196
RAW MATH = 6.4 weeks
VELOCITY
20 points/week
196/20 = 9.8 weeks!

## Slide 30
196
RAW MATH = 6.4 weeks
VELOCITY = 9.8 weeks
MAINTENANCE
3 points/week
Velocity = 17/week
196/17= 11.5 weeks!

## Slide 32
196
RAW MATH = 6.4 weeks
VELOCITY = 9.8 weeks
MAINTENANCE = 11.5 weeks
UNKNOWNS
35% increase!
196 * .35 = 67.55
196 + 67.55 = 263.55
263.55/17 = 15.5 weeks!

## Slide 34
196
RAW MATH = 6.4 weeks
VELOCITY = 9.8 weeks
MAINTENANCE = 11.5 weeks
UNKNOWNS = 15.5 weeks
DAYS OFF
Thanksgiving = 1 week
Vacations/Sick = 1 week
Total = 17.5 weeks

## Slide 36
196
RAW MATH = 6.4 weeks
VELOCITY = 9.8 weeks
MAINTENANCE = 11.5 weeks
UNKNOWNS = 15.5 weeks
DAYS OFF = 17.5 weeks
QUALITY ASSURANCE
Regression Testing & Cleanup = 1 week
Total = 18.5 weeks!

## Slide 38
PLAN FOR
HISTORICAL VELOCITY
MAINTENANCE
UNKNOWNS
DAYS OFF
QUALITY ASSURACE

## Slide 41: COCOMO II

## Slide 42: COCOMO II

## Slide 43: The Development Mode

## Slide 44: The Development Mode

## Slide 45: Modes

## Slide 46: Modes

## Slide 47: Cost Estimation Process
Cost = Size of the Project * Productivity

## Slide 48: Basic COCOMO Model
Computes software development effort (and cost) as function of program size expressed in estimated lines of code
Model
Category | Ab | Bb | Cb | Db
Organic | 2.4 | 1.05 | 2.5 | 0.38
Semi-detached | 3.0 | 1.12 | 2.5 | 0.35
Embedded | 3.6 | 1.20 | 2.5 | 0.32

## Slide 49: Basic COCOMO Equations
Where
  E is effort in person-months
  D is development time in months
  KLOC is estimated number of line of codes

## Slide 50
P = E/D
P total number of persons required to accomplish the project

## Slide 51: Example